## Schedule
구디아카데미 멘토링 3조 프로젝트 개발 일정
By Task
WBS | WBS | Task | Days | Resource | Start Date | Finish Date | Status | Progress | Remain | Priority | Phase | Category | Comments | Holiday
1.1 |  | 분석 설계 | 14 |  | 2021-12-21 | 2021-12-24 |  |  | 1 |  |  |  |  | 2021-01-01
1.1 | 1 | WBS 작성 | 2 | 3조전체 | 2021-12-21 | 2021-12-22 | Close | 100% | 0 |  | 1 |  |  | 2021-02-11
1.1 | 2 | 데이터 테이블 분석 | 4 | 3조전체 | 2021-12-21 | 2021-12-24 | Close | 100% | 0 |  | 1 |  |  | 2021-02-12
1.1 | 3 | 화면 설계서 분석 | 4 | 3조전체 | 2021-12-21 | 2021-12-24 | Close | 100% | 0 |  | 1 |  |  | 2021-03-01
1.1 | 4 | Framework 개발 및 환경 구축 | 4 | 3조전체 | 2021-12-21 | 2021-12-24 | Proc | 75% | 1 |  | 1
1.2 |  | 생산관리 | 12 |  | 2021-12-27 | 2021-12-30 |  |  | 12
1.2 | 1 | 공정 설정 | 2 | 송기문 | 2021-12-27 | 2021-12-28 |  | 0% | 2 |  | 1
1.2 | 2 | 품번 설정 | 2 | 이민희 | 2021-12-27 | 2021-12-28 |  | 0% | 2 |  | 1
1.2 | 3 | 품번 공정 관계 설정 | 2 | 이민희 | 2021-12-29 | 2021-12-30 |  | 0% | 2 |  | 1
1.2 | 4 | 작업지시 관리 | 2 | 송기문 | 2021-12-29 | 2021-12-30 |  | 0% | 2 |  | 1
1.2 | 5 | BOM 설정 | 2 | 장건희 | 2021-12-27 | 2021-12-28 |  | 0% | 2 |  | 1
1.2 | 6 | 창고 설정 | 2 | 장건희 | 2021-12-29 | 2021-12-30 |  | 0% | 2 |  | 1
1.3 |  | 보안 | 4 |  | 2021-12-27 | 2021-12-30 |  |  | 4
1.3 | 1 | 사용자 그룹 설정 | 2 | 이홍직 | 2021-12-27 | 2021-12-28 |  | 0% | 2 |  | 1
1.3 | 2 | 사용자 설정 | 2 | 이홍직 | 2021-12-29 | 2021-12-30 |  | 0% | 2 |  | 1
1.4 |  | 영업관리 | 4 |  | 2021-12-31 | 2022-01-05 |  |  | 4
1.4 | 1 | 제품 주문 | 2 | 송기문 | 2021-12-31 | 2022-01-03 |  | 0% | 2 |  | 1
1.4 | 2 | 완제품 출하 | 2 | 송기문 | 2022-01-04 | 2022-01-05 |  | 0% | 2 |  | 1
1.5 |  | 구매관리 | 2 |  | 2021-12-31 | 2022-01-03 |  |  | 2
1.5 | 1 | 자재 구매 입고 | 2 | 장건희 | 2021-12-31 | 2022-01-03 |  | 0% | 2 |  | 1
1.6 |  | 품질관리 | 4 |  | 2021-12-31 | 2022-01-05 |  |  | 4
1.6 | 1 | 검사 항목 설정 | 2 | 이홍직 | 2021-12-31 | 2022-01-03 |  | 0% | 2 |  | 1
1.6 | 2 | 검사 공정관계 설정 | 2 | 이홍직 | 2022-01-04 | 2022-01-05 |  | 0% | 2 |  | 1
1.7 |  | 생산관리-POP | 16 |  | 2021-12-31 | 2022-01-11 |  |  | 16
1.7 | 1 | 생산 LOT 생성 | 2 | 이민희 | 2021-12-31 | 2022-01-03 |  | 0% | 2 |  | 1
1.5 | 2 | LOT 상태 및 이력조회 | 2 | 이민희 | 2022-01-04 | 2022-01-05 |  | 0% | 2 |  | 1
1.5 | 3 | 생산 LOT 작업 시작 | 2 | 이홍직 | 2022-01-06 | 2022-01-07 |  | 0% | 2 |  | 1
1.5 | 4 | 검사 데이터 입력 | 2 | 이홍직 | 2022-01-10 | 2022-01-11 |  | 0% | 2 |  | 1
1.5 | 5 | 생산 LOT 자재 사용 | 2 | 송기문 | 2022-01-06 | 2022-01-07 |  | 0% | 2 |  | 1
1.5 | 6 | 생산 LOT 작업 완료 | 2 | 송기문 | 2022-01-10 | 2022-01-11 |  | 0% | 2 |  | 1
1.5 | 7 | 생산 LOT 불량 등록 | 2 | 장건희 | 2022-01-04 | 2022-01-05 |  | 0% | 2 |  | 1
1.5 | 8 | 생산 비가동 등록 | 2 | 장건희 | 2022-01-06 | 2022-01-07 |  | 0% | 2 |  | 1 |  | 설계서의 설비 비가동이 아닌 일자의 생산 비가동만을 등록
1.8 |  | 리포트 - WEB | 11 |  | 2022-01-06 | 2022-01-12 |  |  | 11
1.8 | 1 | 계획대비 생산 실적 조회 | 2 | 이민희 | 2022-01-06 | 2022-01-07 |  | 0% | 2 |  | 1
1.8 | 2 | 제조 종합 효율 조회 | 2 | 이민희 | 2022-01-10 | 2022-01-11 |  | 0% | 2 |  | 1
1.8 | 3 | 검사 데이터 조회 | 1 | 이민희 | 2022-01-12 | 2022-01-12 |  | 0% | 1 |  | 1
1.8 | 4 | LOT 이력 조회 | 2 | 장건희 | 2022-01-10 | 2022-01-11 |  | 0% | 2 |  | 1 |  | 자재 사용 이력 포함
1.8 | 5 | 제품 재고 조회 | 1 | 장건희 | 2022-01-12 | 2022-01-12 |  | 0% | 1 |  | 1 |  | 공정의 LOT 목록 조회
1.8 | 6 | 창고 재고 조회 | 1 | 송기문 | 2022-01-12 | 2022-01-12 |  | 0% | 1 |  | 1 |  | 창고의 재고 LOT 목록 조회
1.8 | 7 | 자재 투입 이력 조회 | 1 | 이홍직 | 2022-01-12 | 2022-01-12 |  | 0% | 1 |  | 1 |  | 생산 LOT 에 자재 LOT 투입 이력 조회
1.8 | 8 | 불량 이력 조회 | 1 | 송기문 | 2022-01-12 | 2022-01-12 |  | 0% | 1 |  | 1 |  | 일자별 불량 유형 조회
2.1 |  | 프로그램 최종 테스트 | 2 |  | 2022-01-13 | 2022-01-13 |  |  | 2
2.1 | 1 | 모듈 간 연동 테스트 | 1 | 3조전체 | 2022-01-13 | 2022-01-13 |  | 0% | 1 |  | 1
2.1 | 2 | 유효성 검사 및 버튼 기능 검사 | 1 | 3조전체 | 2022-01-13 | 2022-01-13 |  | 0% | 1 |  | 1
Formulas:
Start Date = MIN([Start Date, row below]:F9)
Start Date = MIN([Start Date, row below]:[Start Date, row below])
Finish Date = MAX([Finish Date, row below]:G9)
Finish Date = IF([Days] >= 1, WORKDAY([Start Date],([Days] -1),O5:O12), WORKDAY([Start Date],[Days],O5:O12))

## Summary
구디아카데미 멘토링 프로젝트 개발 일정
[6 empty] | 업데이트 | 2021-12-21
일정 종합
| Items |  | Issue Items | Complete Items | Estimation (M/D) | Remaining Efforts (M/D) | Progress (M/D) | Progress (%) | Developer | Issue Items | Complete Items | Estimation (M/D) | Remaining Efforts (M/D) | Progress (M/D) | Progress (%)
| Total |  | 35 | 3 | 69 | 56 | 13 | 18.84% | Total | 35 | 3 | 69 | 56 | 13 | 18.84%
| By Group | [7 empty] | By Developer
| WBS | Items | Issue Items | Complete Items | Estimation (M/D) | Remaining Efforts (M/D) | Progress (M/D) | Progress (%) | Developer | Issue Items | Complete Items | Estimation (M/D) | Remaining Efforts (M/D) | Progress (M/D) | Progress (%)
| 1.1 | 분석 설계 | 4 | 3 | 14 | 1 | 13 | 92.86% | 송기문 | 8 | 0 | 14 | 14 | 0 | 0%
| 1.2 | 생산관리 | 6 | 0 | 12 | 12 | 0 | 0% | 이민희 | 7 | 0 | 13 | 13 | 0 | 0%
| 1.3 | 보안 | 2 | 0 | 4 | 4 | 0 | 0% | 이홍직 | 7 | 0 | 13 | 13 | 0 | 0%
| 1.4 | 영업관리 | 2 | 0 | 4 | 4 | 0 | 0% | 장건희 | 7 | 0 | 13 | 13 | 0 | 0%
| 1.5 | 구매관리 | 8 | 0 | 2 | 2 | 0 | 0% | 3조전체 | 6 | 3 | 16 | 3 | 13 | 81.25%
| 1.6 | 품질관리 | 2 | 0 | 4 | 4 | 0 | 0% | x | 0 | 0 | 0 | 0 | 0 | 0%
| 1.7 | 생산관리-POP | 1 | 0 | 16 | 16 | 0 | 0% | x | 0 | 0 | 0 | 0 | 0 | 0%
| 1.8 | 리포트 - WEB | 8 | 0 | 11 | 11 | 0 | 0% | x | 0 | 0 | 0 | 0 | 0 | 0%
| 2.1 | 프로그램 최종 테스트 | 2 | 0 | 2 | 2 | 0 | 0%
|  |  | 0 | 0 | 0 | 0 | 0 | 0%
|  |  | 0 | 0 | 0 | 0 | 0 | 0%
|  |  | 0 | 0 | 0 | 0 | 0 | 0%
|  |  | 0 | 0 | 0 | 0 | 0 | 0%
|  |  | 0 | 0 | 0 | 0 | 0 | 0%
|  |  | 0 | 0 | 0 | 0 | 0 | 0%
|  |  | 0 | 0 | 0 | 0 | 0 | 0%
|  |  | 0 | 0 | 0 | 0 | 0 | 0%
|  |  | 0 | 0 | 0 | 0 | 0 | 0%
|  |  | 0 | 0 | 0 | 0 | 0 | 0%
|  |  | 0 | 0 | 0 | 0 | 0 | 0%
|  |  | 0 | 0 | 0 | 0 | 0 | 0%
|  |  | 0 | 0 | 0 | 0 | 0 | 0%
|  |  | 0 | 0 | 0 | 0 | 0 | 0%
|  |  | 0 | 0 | 0 | 0 | 0 | 0%
|  |  | 0 | 0 | 0 | 0 | 0 | 0%
|  |  | 0 | 0 | 0 | 0 | 0 | 0%
|  |  | 0 | 0 | 0 | 0 | 0 | 0%
|  |  | 0 | 0 | 0 | 0 | 0 | 0%

## Resource
Resource List
Resource | Resource | Resource | Resource | Resource | Resource | Resource | Resource | Resource | Resource | Resource | Resource | Resource | Resource | Resource | Resource | Resource | Resource | Resource | Resource | Resource | Resource | Resource | Resource | Resource | Resource
송기문 | 이민희 | 이홍직 | 장건희 | 3조전체 | x | x | x | x